* **Estimation of Digital Discount Card Project:**

**Initiation Phase:**

|  |  |
| --- | --- |
| **Work Package** | **Duration Estimation** |
| **Evaluation & Recommendations** | **1 day** |
| **Develop Project Charter** | **2 days** |
| **Deliverable: Submit Project Charter** | **0.5 day** |
| **Project Sponsor Reviews Project Charter** | **0.5 day** |
| **Total Estimation: 4 days** | |

**Planning Phase:**

|  |  |
| --- | --- |
| **Work Package** | **Duration Estimation** |
| **Create Preliminary Scope Statement** | **1 day** |
| **Determine Project Team** | **0.5 day** |
| **Project Team Kickoff Meeting** | **0.5 day** |
| **Develop Project Plan** | **3 days** |
| **Total Estimation: 5 days** | |

**Execution Phase:**

|  |  |
| --- | --- |
| **Work Package** | **Duration Estimation** |
| **Project Kickoff Meeting** | **0.5 day** |
| **Verify & Validate User Requirements** | **1.5 day** |
| **Design System** | **15 days** |
| **Software Development** | **30 days** |
| **Deploy Development System** | **0.5 day** |
| **Testing Phase** | **6 days** |
| **Deploy Live System** | **0.5 day** |
| **User Training** | **3 days** |
| **Total Estimation: 57 days** | |

**Closeout Phase:**

|  |  |
| --- | --- |
| **Work Package** | **Duration Estimation** |
| **Document Lessons Learned** | **1 day** |
| **Update Records** | **1 day** |
| **Gain Formal Acceptance** | **2 days** |
| **Total Estimation: 4 days** | |

**Total Estimation of project: 70 days**

**Assumptions:**

1. **Number of development team members are five team members with previous background in developing similar projects**
2. **Fridays and Saturdays are off work**
3. **All PM and Project teams have previous experience**